## Foglio1
SPRINT 9 - TIMESHEET
| see consultants' statistic widget | new design adaptation | delete a consultant | Consultant consultant page | BM consultant page | mofidy consultants | list of consultants | Create a consultant
Amedeo | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 11
Charly | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 0
Saurav | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
Gregory | 0 | 0 | 0 | 13 | 10 | 0 | 0 | 30
Maxime | 8 | 0 | 2 | 1 | 0 | 5 | 12 | 0
Elisa | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0
Total amount | 8 | 21 | 13 | 14 | 10 | 8 | 17 | 59
charly 11/07
FEEDBACK COLLECTION
STORY | ESTIMATION | BAD ESTIMATED (yes/no, under/over, indicator)
Create a consultant | 8 | yes, underestimated, new_func | required a lot of effort unexpected, in particular for the grpc connection
List of consultants | 3 | no
Modify consultant | 2 | no
Consultant page for BM | 2 | no
Consultant page for Consultant | 2 | no
Delete a consultant | 3 | no
See consultants' statistic widget | 2 | no
new design adaptation | 5 | no
Possible indicators | short name
user story is a spike | spike
user story requires new technology | new_tech
user story begins a new set of functionalities | new_func
other | other