## Slide 1: First results presentation
Amedeo Sarpa 281638

## Slide 2
Intro
This short presentation shows data collected during the first 4 sprints of the development of a web application in an agile team (all interns)
Each table is followed by a little analysis of the outcomes

## Slide 3
Outline
Chart Variance in estimates
Correlation coefficient and feedbacks
Future works

## Slide 4
Outline
Chart Variance in estimates
Correlation coefficient and feedbacks
Future works

## Slide 5
Chart Variance in estimates
In the next slide is showed the ‘chart variance in estimates’, that we used as a possible metrics to determine if an user story was under/over estimated.
Since we estimate stories following the Fibonacci series in the range [1,13],
for each story point we took track of the effort in hour. Then for each story point category we compute the median and the deviation standard : An user story of a certain category is bad estimated if its effort is outside the interval centered in the median of the catregory and large one standard deviation.
For example, for the category of user story estimated 8, the median is 28h and the standard deviation is approximately 6. The interval is [22,34], so an user story estimated 8 with an effort of 40h, is overstimated.

## Slide 6
Chart Variance in estimates
The most significant results come from category of user stories estimated 5 :
Is the category with the largest number of story bad estimated
The median is higher of the median of user stories estimated as 8
The two stories which effort is close to the median value, so it fits well in the category, for the team were considered as underestimated (more details about in the next slides)

## Slide 7
Chart Variance in estimates
Here are showed the list of user story bad estimated detected by the metric afromentioned.
User Story | #Sprint | Estimation | Under/Over
Create helm chart and deploy | 3 | 2 | Under
Restyle of user interface | 3 | 5 | Under
Create a reward | 3 | 3 | Under
Filter functionalities by role | 3 | 5 | Over
Request for an activity | 4 | 5 | Under
See Alten grains points | 4 | 1 | Under
Accept or reject a request | 4 | 3 | Under
Give Alten grains | 5 | 8 | Over

## Slide 8
Chart Variance in estimates
However, the metric afromentioned could be prone to errors, like of bias selection. So with the team we also decided to determine if an user story was under/over estimated. We individuated 6 more user stories bad estimated (showed in this table), and one user story that for the metric is underestimated, but for the team is not (the one marked at the bottom).
User Story | #Sprint | Estimation | Under/Over
Cancel request | 4 | 3 | Under
Learn React query and apply it | 4 | 5 | Under
Send notification | 5 | 5 | Under (for the metric fit well instead)
Print notification | 5 | 5 | Under (for the metric fit well instead)
Give feedback after action executed | 5 | 3 | Under
Filter of pending requests | 5 | 3 | Over
Event date in the requests list | 6 | 2 | Under
Validation popup | 6 | 2 | Under
See Alten grains points | 4 | 1 | Under

## Slide 9
Outline
Chart Variance in estimates
Correlation coefficient and feedbacks
Future works

## Slide 10
Correlation coefficient and feedbacks
We tried to individuate some possible indicators that causes user story’s bad estimation. The possible indicators analysed are :
User Story starts a set of new functionalities
User Story requires the application of new technologies not used so far
Spike Story, that requires not only working code but to learn something new.
To check if some of the these three just mentioned is a possible indicator for bad estimation, we compute the correlation coefficient between each indicators and the user stories considered under/over estimated by the team Furthermore, we collect and count feedbacks occurences from each member about the reasons of bad estimation (beyond those that may be due to the 3 indicators)

## Slide 11
Correlation coefficient and feedbacks
The table illustrates the correlation coefficient for each indicator. Since this value is bounded between [-1,1], The first indicator’s correlation value is very weak, while for the ‘new technology’ and for the ‘spike’ there is a moderate correlation. In particular, user stories bad estimated that are spike and/or requires the use of new technologies, were all underestimated. Probably beacuse we got a lot of comments on the merge requests since was the first time we used these technologies, and so the effort in hours grow up.
Indicator | Coefficient value
New functionalities | 0.16
New technology | 0.59
Spike story | 0.48

## Slide 12
Correlation coefficient and feedbacks
Is relevant that if an user story is not clear during the planning, can lead to under/over estimation. So It’s important that the user story is well defined (with its Acceptance Criteria) and that during the planning we have all a clear of the goal of the story.
Description | Total occurences | Under estimation occurrences | Over estimation occurrences
Difficult in testing | 1 | 1 | -
User story not clear during the planning | 9 | 6 | 3
Difficult in the implementation | 1 | 1 | -
Client needs not clear | 1 | 1 | -
Code review take a lot of time | 1 | 1 | 0
This table shows feedback provided by developers about user story bad estimated, with the occurences per each one.

## Slide 13
Outline
Chart Variance in estimates
Correlation coefficient and feedbacks
Future works

## Slide 14
Future works
We will continue to collect this data to see if, after analysis and discussion of the results seen so far, there will be improvements in the process.

## Slide 15
References
Link to the github repo where you can find all data:
https://github.com/AmedeoSarpa/thesis