## Foglio1
SPRINT 4 - TIMESHEET
| Request for activity grains | See points | Accept or deny request | cancel request | see pending request | learn react query and apply to the project | review and update the c4 model and functional diagram | request for reward | -
Amedeo | 16 | 0 | 14 | 14 | 0 | 0 | 0 | 1 | 0
Charly | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
Elisa | 26 | 0 | 0 | 0 | 0 | 12 | 12 | 4 | 0
Gregory | 5 | 5 | 0 | 0 | 16 | 15 | 0 | 0 | 0
Maxime | 0 | 0 | 30 | 4 | 2 | 7 | 0 | 0 | 0
Total amount | 47 | 5 | 44 | 18 | 18 | 34 | 19 | 5 | 0
FEEDBACK COLLECTION
Reasons why a user story was under/over stimated
STORY | ESTIMATION | BAD ESTIMATED | REASONS
Request for activity grains | 5 | yes, underestimated | Client wanted for this page a lot of feature (e.g. popup pages) that create a sort of confusion during the front-end developing. Even in back-end, passed some times before we got the solution of pending grains amount, to manage case when a consultant request for an activity but has no enough points
See points | 1 | no
Accept or deny request | 3 | yes, underestimated | We did not thought during the plannig that every time a request is accepted or not, we had to manage some other things like the amount of grains and the pending grains.
cancel request | 3 | yes, underestimated | We did not took in consideration during the planning that noSQL has no join operations and no cascade operations.
see pending request | 5 | no
learn react query and apply to the project | 5 | yes,underestimated | Was hard to learn and apply this big library to the project. Even beacuase we had a lot of comments during the code review beacuse we did not understood well on how to use it.
review and update the c4 model and functional diagram | 5 | no
Request for reward | 2 | no