## Foglio1
SPRINT 3 - TIMESHEET
|  | create helm chart and deploy the Rewards | restyle of user interface | create a reward | view list of rewards | modify a reward | delete a reward | filter functionalities by role | see alten point | create a request | accept or deny a request
Amedeo |  | 0 | 0 | 18 | 2 | 4 | 2 | 4 | 0 | 0 | 0
Charly |  | 9 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
Elisa |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gregory |  | 21 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maxime |  | 20 | 0 | 7 | 6 | 6 | 1 | 0 | 0 | 0 | 0
Total amount |  | 50 | 57 | 25 | 8 | 10 | 3 | 8 | 0 | 0 | 0
FEEDBACK COLLECTION
STORY | ESTIMATION | BAD ESTIMATED(yes/no;under/over;indicator) | REASONS
create helm chart and deploy the Rewards | 2 | yes; underestimated;spike | Since we wanted to introduce Gregory in the cloud development, explain to him how to create an helm chart took more time than expected
restyle of user interface | 5 | yes; underestimated;spike,new_tech | Since we decided to use MUI, in some cases just a base knowledge was enough in other a deeper knowledge (that we did not had) was needed.
create a reward | 3 | yes, underestimated;new_func | We did not had clear idea on the implementation and on the data model, so we changed a lot of times our implementation.
view list of rewards | 3 | no
modify a reward | 3 | no
delete a reward | 2 | no
filter functionalities by role | 5 | yes,overestimated;other | During the planning the goal of this story was not clear, so probably, with the fear of underestimating, we put 5. At the end was just the implementation of a function to decide the visibility of button in the sidebar, basing on the user role.
Possible indicators | short name
user story is a spike | spike
user story requires new technology | new_tech
user story begins a new set of functionalities | new_func
other | other