## Foglio1
SPRINT 5 - TIMESHEET
| Check history of the grains | give alten grains | send notifications | filters for the view of pending request | print notifications | show title of a page in the navbar | give feedback when user performs an action
Amedeo | 2 | 4 | 28 | 0 | 7 | 0 | 0
Charly | 0 | 0 | 0 | 3 | 0 | 0 | 0
Elisa | 0 | 10 | 0 | 0 | 0 | 1 | 0
Gregory | 0 | 4 | 0 | 0 | 23 | 0 | 15
Maxime | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total amount | 2 | 18 | 28 | 3 | 30 | 1 | 15
FEEDBACK COLLECTION
STORY | ESTIMATION | BAD ESTIMATED (yes/no, under/over, indicator) | REASONS
Check history of the grains | 1 | no
give alten grains | 8 | yes;overestimated;other | During the planning since we did not had the code of the creation for a request in front of us, we did not thouht that could be imlpemented as a creation for a request but with the state directly set to 'approved'.
send notifications | 5 | yes;underestimated;new_tech,new_func,spike | We did not thought during the planning that this required the interactions between microservice, so we had to use the gRPC protocol, that was new to everyone
filters for the view of pending request | 3 | yes;overestimated;other | During planning we did not had clear idea on how to implement this (in back-end or front-end). Since we decided to implement it in front-end, implementation was very easy, just a matter of add a filter in the list.
print notifications | 5 | yes; underestimated;spike,new_tech,new_func | Create the notification panel, with the list of notifications and the possibility to have the number of unread notificiation on the bell, took more than expected.
show title of a page in the navbar | 2 | no
give feedback when user performs an action | 3 | yes; underestimated;spike | Required the usage of a new functionalities of react query that we use for the first time
Possible indicators | short name
user story is a spike | spike
user story requires new technology | new_tech
user story begins a new set of functionalities | new_func
other | other