## Foglio1
SPRINT 6 - TIMESHEET
| Add grains in reward and activities page | Event date in request for activities | Validation popup for actions | Possibility to delete a tenant | Search for widgets | Add widget to the dashboard | delete widgets | save widget position | suggest activity
Amedeo | 0 | 6 | 0 | 11 | 2 | 13 | 2 | 13 | 0
Charly | 0 | 13 | 0 | 0 | 0 | 4 | 0 | 1 | 6
Elisa | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gregory | 0 | 0 | 14 | 0 | 14 | 14 | 0 | 12 | 4
Maxime | 3 | 2 | 0 | 0 | 14 | 2 | 11 | 0 | 0
Total amount | 3 | 21 | 14 | 11 | 30 | 33 | 13 | 26 | 10
FEEDBACK COLLECTION
STORY | ESTIMATION | BAD ESTIMATED (yes/no, under/over, indicator) | REASONS
Add grains in reward and activities page | 1 | no
Event date in request for activities | 2 | yes;underestimated;other | We did not took in consideration to add the 'tag' in the notification data model. We encoutereed also some difficulites in testing
Validation popup for actions | 2 | yes;underestimated;other | We had problems with test, in particular with snapshots.
Possibility to delete a tenant | 3 | no
Search for widgets | 8 | no
Add widget to the dashboard | 8 | no
delete widgets | 3 | no
save widget position | 8 | no
suggest activity | 3 | no
Possible indicators | short name
user story is a spike | spike
user story requires new technology | new_tech
user story begins a new set of functionalities | new_func
other | other